## Form Responses
Timestamp | Email Address | NetID | Responsible Team | Current Status | Photo Upload | Issue Description | Required Actions / Comments | Email Tracking | Deadline | Cleared
2025-09-18 09:20 | Nhh5@cornell.edu | Nhh5 | steel bridge | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1o2qJINxEtIWecc01_T3hwMHrd5eQW7Di | Housekeeping | Move workbenches and materials At least a foot away from air tunnel | Old | 2025-09-28 | 2025-10-01
2025-09-18 09:24 | Nhh5@cornell.edu | Nhh5 | concrete canoe | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1Cj39FQhlasJjzh3Sf41upPlEaOf7NAC0 | Shared space (misuse of) | Clear floor in storage area. | Old | 2025-09-28 | 2025-10-01
2025-09-18 09:29 | Nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1Mc8D5g7mozMYaAZcBsNgDAp901dBI9qT | Shared space (misuse of) | Clear floor in storage area. | Old | 2025-09-28 | 2025-10-01
2025-09-18 09:33 | Nhh5@cornell.edu | Nhh5 | concrete canoe | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1fUkZ-J4_Kys5RAB58s01JW6v30eo9AzT | Housekeeping | Empty trash barrels in HVL | Email Sent | 2025-09-28 | 2025-10-01
2025-09-18 14:54 | Nhh5@cornell.edu | Nhh5 | Formula | Orange - Operations/ Safety issue (resolve in 2-3 business days) | https://drive.google.com/open?id=19rnv4vGnF9Xt7ZLx48vzx5YO834_awAw | Shared space (misuse of) | Move tables, coolers and canopy to penthouse | Email Sent | 2025-09-21 | 2025-10-01
2025-09-19 17:15 | Nhh@cornell.edu | Nhh | concrete canoe | Red - Code violation (immediate action Required) | https://drive.google.com/open?id=1sVyU0mTazSzHvLjUdiOo4fX2uiTrtypC | Fire / electrical (code violation) | Move | Email Sent | 2025-09-20 | 2025-10-01
2025-10-02 15:18 | Nhh5@cornell.edu | Nhh5 | Mars Rover | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=15i9xzSWFPv9z9PeIcUNKH3ssC5nyvKvo | Egress / access | Move tool box from aisle | Email Sent | 2025-10-12 | 2025-10-08
2025-10-02 16:41 | jam834@cornell.edu | jam834 | DEBUT | Red - Code violation (immediate action Required) | https://drive.google.com/open?id=1fxgTpXNCdpgbdzmNTtu4HbDfrWtOJMTn | Fire / electrical (code violation) | Move item away from electrical panel — area must be kept clear. | Email Sent | 2025-10-03 | 2025-10-08
2025-10-03 09:13 | Nhh5@cornell.edu | Nhh5 | Operations Team | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1zTyHKHLN7vLoIi779WHc-U8YZIlEwKP4 | Unsafe Work Practices | Fix pedestal vise. | Email Sent | 2025-10-13 | 2025-10-08
2025-10-03 09:30 | Nhh5 @cornell.edu | Nhh5 | Operations Team | Ivory - Below standard (demonstrate improvement in 14-21 days) | https://drive.google.com/open?id=13kUfFEkdHXepwkLwBTjrBuajGaT-xZnY | Maintenance/ facilities | Set up new vacuum pump. Move old smoky to HVL | Email Sent | 2025-10-24 | 2025-10-08
2025-10-03 09:33 | Nhh5 @cornell.edu | Nhh5 | Operations Team | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=16l_X5ZpmGtHh75Hv4Up14_pg8mO5oAUz | Unsafe Work Practices | Store respirators in appropriate containers | Email Sent | 2025-10-13 | 2025-10-08
2025-10-03 09:35 | Nhh5 @cornell.edu | Nhh5 | Operations Team | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1dvJfl4IevUW-CeIfsjhePDQVPw3-OvXw | Fire / electrical (code violation) | Source replacement code compliant power supply | Email Sent | 2025-10-13 | 2025-10-08
2025-10-03 09:40 | Nhh5 @cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1de8HXNiKxiP1EIAvmTIH2ArUK5_RiVSZ | Maintenance/ facilities | Devise integrated storage mount for brushes and dust pans along with brooms. | Email Sent | 2025-12-02 | 2025-10-08
2025-10-06 09:48 | Nhh5@cornell.edu | Nhh5 | Mars Rover | Orange - Operations/ Safety issue (resolve in 2-3 business days) | https://drive.google.com/open?id=1EigQr0yz4Nf_iDZNasaNwNT5iYrfuBjB | Egress / access | Remove carts from main hall | Email Sent | 2025-10-09 | 2025-10-08
2025-10-07 12:32 | Nhh5@cornell.edu | Nhh5 | Operations Team | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1vneF2OPeq9ClRfKJh2-2CwxVGO2jfGyO | Housekeeping | Clear workbench. | Email Sent | 2025-10-17 | 2025-10-08
2025-10-13 09:56 | Nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship concern (Address at next scheduled meeting) | https://drive.google.com/open?id=1ZjqE0xFBW0lrlbBGK6ncoZ3rXCgOPV5C | Shared space (misuse of) | Store material in cages or HVL racks | Email Sent | 2025-10-23 | 2025-10-15
2025-10-13 09:59 | Nhh5@cornell.edu | Nhh5 | Baja | Orange - Operations/ Safety issue (resolve in 2-3 business days) | https://drive.google.com/open?id=1k8S-vzReA0gG3pY4Fibg1-_oiV_7KZVJ | Fire / electrical (code violation) | Learn access to panel and eye wash. | Email Sent | 2025-10-16 | 2025-10-15
2025-10-16 16:21 | jam834@cornell.edu | jam834 | Operations Team | Red - Code violation (same day action Required) |  | Egress / access | Engine crane, whiteboard, and chair cannot be left in front of electrical panel / yellow walkway. | Email Sent | 2025-10-17 | 2025-10-17
2025-10-20 09:15 | nhh5@cornell.edu | nhh5 | Baja | Red - Code violation (same day action Required) | https://drive.google.com/open?id=18iOgpD_uJExXfOEng28xarrcXyN9R2xz | Fire / electrical (code violation) | Chain compressed gas cylinder to table leg | Email Sent | 2025-10-21 | 2025-10-20
2025-10-22 14:01 | Nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1rD264d84PD7vjcoJN8BPcJsPtTNfB0WK | Maintenance/ facilities | Design better vertical storage for sheet goods. 4‘ x 8‘. | Old | 2025-12-21
2025-10-22 14:03 | Nhh5@cornell.edu | Nhh5 | Operations Team | Ivory - Below standard (demonstrate improvement in 14-21 days) | https://drive.google.com/open?id=1A97dmPWHNR31nQhwDIxersrMv-w3rTrW | Maintenance/ facilities | Replace paint booth exhaust filters | Jatin and Eve took it on | 2025-11-12 | 2025-11-03
2025-10-29 09:02 | Nhh5@cornell.edu | Nhh5 | Baja | Orange - Operations/ Safety issue (resolve in 2-3 business days) |  | Unsafe Work Practices | Get welder cables off floor. | Email Sent | 2025-11-01 | 2025-11-01
2025-10-29 09:03 | Nhh5@cornell.edu | Nhh5 | Baja | Red - Code violation (same day action Required) | https://drive.google.com/open?id=1-7XqwdVL-j4aeqhs3MK4XY0jOus6LqOs | Egress / access | Clear access areas | Email Sent | 2025-10-30 | 2025-10-30
2025-10-29 09:04 | Nhh5@cornell.edu | Nhh5 | Baja | Red - Code violation (same day action Required) | https://drive.google.com/open?id=1C2O9zg0kXZ8vKHEdR54vLTMAKOfPGGcS | Fire / electrical (code violation) | Store gas cans in flammables cabinet | Email Sent | 2025-10-30 | 2025-10-30
2025-10-29 09:05 | Nhh5@cornell.edu | Nhh5 | Formula | Red - Code violation (same day action Required) | https://drive.google.com/open?id=1Djirgeu3f7r4fq4Xcew83PfEAO4Qsy5s | Fire / electrical (code violation) | Clear area in front of fire extinguisher | Email Sent | 2025-10-30 | 2025-10-30
2025-10-29 16:11 | Nhh5@cornell.edu | Nhh5 | Operations Team | Yellow - Stewardship concern (resolve in 7-10 days) | https://drive.google.com/open?id=1TUZqpxJrsyJtnjf-jPi1ro9-BRdytLcd | Egress / access | Pick up stones from pavement and put them on island closer to the auto lab door so they don’t roll off again. | Email Sent | 2025-11-08 | 2025-11-01
2025-10-31 09:12 | Nhh5@cornell.edu | Nhh5 | CUAir | Yellow - Stewardship concern (resolve in 7-10 days) |  | Shared space (misuse of) | Store Orion parts in team space not in front of shared equipment. | Email Sent | 2025-11-10 | 2025-11-11
2025-10-31 09:18 | Nhh5@cornell.edu | Nhh5 | Operations Team | Orange - Operations/ Safety issue (resolve in 2-3 business days) | https://drive.google.com/open?id=1rGDOeXchU_75BhP1HMOPWZ1q2L3BoXaP | Unsafe Work Practices | Secure lumber so it won’t fall and ID owners to advise same. |  | 2025-11-03 | 2025-11-04
2025-10-31 09:21 | Nhh5@cornell.edu | Nhh5 | Operations Team | Yellow - Stewardship concern (resolve in 7-10 days) | https://drive.google.com/open?id=1zYjmdJ0ZSWGRYxppxo0OuO_TA1SGLH5j | Housekeeping | Clear floor around workbench |  | 2025-11-10 | 2025-11-10
2025-10-31 09:28 | Nhh5@cornell.edu | Nhh5 | Baja | Yellow - Stewardship concern (resolve in 7-10 days) | https://drive.google.com/open?id=1D3qL8TNVc7-zvT5jNVjWzs4qgRazBxpV | Housekeeping | Please empty cabinet for relocation | Email Sent | 2025-11-10
2025-11-06 13:03 | Nhh5@cornell.edu | Nhh5 | Baja | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1o7d5biGDr7eD_qug17NvNQh1fYBUj_5q | Unsafe Work Practices | Test | Email Sent | 2026-01-05 | 2025-11-05
2025-11-06 13:41 | Nhh5@cornell.edu | Nhh5 | CUAir | Ivory - Below standard (demonstrate improvement in 14-21 days) | https://drive.google.com/open?id=1yaJWGvoit8IELsPGJon8Uot_H55H-3Xt | Housekeeping | Clean up composites corner to improve access and organization | Email Sent | 2025-11-27
2025-11-06 13:44 | Nhh5 @cornell.edu | Nhh5 | CEV | Yellow - Stewardship concern (resolve in 7-10 days) | https://drive.google.com/open?id=1GU--yibtx14WJZ0_sNuqmbNL8j73iLRt | Shared space (misuse of) | Clear downdraft table when not in use | Email Sent | 2025-11-16 | 2025-11-10
2025-11-10 09:00 | nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1TsTIvzGNhcttVMZnPgTe3qVgU0VsCkeF | Maintenance/ facilities | Remove spray paint from wall outside autolab | Email Sent | 2025-11-20 | 2025-11-11
2025-11-10 10:06 | nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1iomJVuZ19QsXWRUe6B02t_ql9QHyqJTr | Work Practices | Please clear out painted rocks (put in dumpster) | Email Sent | 2025-11-20 | 2025-11-11
2025-11-10 10:12 | nhh5@cornell.edu | Nhh5 | Baja | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1l45SBxHjJXbdD2SEDfSi3sBh1qsgbE6r | Chemical storage | Empty oil into 5gal pail for R5 pickup. | Email Sent | 2025-11-13 | 2025-11-12
2025-11-10 10:29 | nhh5@cornell.edu | Nhh5 | Concrete Canoe | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1kFViKfhSK_t8CK6wcdJdNkaH7GrxyU95 | Egress / access | Assuming this is CCC’s - Move foam to HVL can’t block walkway. | Email Sent | 2025-11-13 | 2025-11-17
2025-11-13 16:27 | jam834@cornell.edu | jam834 | EWH | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=16-2ZzgFD8n9wZYaniPOz0w6NisXEwoO_ | Fire code | Assuming EWH. Wheelchair cannot be in front of the electrical panel. A note has been left on the chair by myself and I moved the chair on one occasion, but it keeps being replaced there. | Email Sent | 2025-11-16
2025-11-13 16:28 | jam834@cornell.edu | jam834 | EWH | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=18GFZyZDJ1WJcR3ieXj1Yw5iJKXofAb_- | Fire code | Assuming EWH. Buckets / boxes cannot be placed in front of electrical panel. | Email Sent | 2025-11-16
2025-11-13 16:29 | jam834@cornell.edu | jam834 | Unknown / unsure | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1mQ8i67BWT-5bGibx-MAF1fsWzVJgi1QP | Fire code | None of the Baja / FSAE team members I've spoken to know whose this crane is, but it is blocking the walkway / electrical panel. I have moved it once before, but it continues to be placed in this spot. |  | 2025-11-16
2025-11-14 17:28 | nhh5@cornell.edu | Nhh5 | Baja | Purple - Opportunity for improvement (as time permits) |  | Housekeeping | Test | Email Sent | 2026-01-13
2025-11-15 12:43 | jam834@cornell.edu | jam834 | Geodata | Yellow - Stewardship Concern (resolve in 7-10 days) |  | Shared space | Boxes appearing to contain geodata materials was placed in front of the EWH shelves. Please refrain from doing so and respect the storage areas of your fellow teams. The boxes were moved in front of the geodata shelves. | Email Sent | 2025-11-25
2025-11-16 09:54 | mcm329@cornell.edu | Mcm329 | Unknown / unsure | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1dNbx1aeoMp1ZXsSz8QghQUrmZj2Meur8 | Fire code | Not sure what these are but one fell. I’m on my way back to pick it up but maybe there’s a better spot to store these? red cause they were blocking the way. ended up having to pick them up twice during my shift |  | 2025-11-17 | 2025-11-17
2025-11-17 14:53 | nhh5@cornell.edu | Nhh5 | Baja | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1PNU5A-0qAHonIszvNFXADK692wlhKOkH | Chemical storage | Keep flammables off welding table/ hot works area and in flammables cabinet when not in use. | Email Sent | 2025-11-20 | 2025-11-18
2025-11-21 14:20 | nhh5@cornell.edu | Nhh5 | Formula | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1hQCTHk3xslj4m24P7CZZmpTwX5Fp_k7c | Work Practices | Please keep door closed (or at least mostly closed) when room is not in use. | Email Sent | 2025-11-24 | 2025-12-03
2025-11-21 14:35 | nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship Concern (resolve in 7-10 days) |  | Housekeeping | Store material rolls so the won’t fall or lean on waste chemical drum | Email Sent | 2025-12-01
2025-12-01 20:02 | nh428@cornell.edu | nh428 | Operations Team | Yellow - Stewardship Concern (resolve in 7-10 days) |  | Housekeeping | Carbon fiber and metal tubes on the right side of B60 on the verge of falling |  | 2025-12-11 | 2025-12-03
2026-01-21 16:18 | nhh5@cornell.edu | Nhh5 | AutoBoat | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=123AIpsKqNibRFF3EB1mKLcqO3XH4F6Ds | Egress / access | Remove materials that are blocking access to flammables cabinets | Email Sent | 2026-01-24
2026-01-21 16:20 | nhh5@cornell.edu | Nhh5 | Formula | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1H96S9ivvB4e3WGdp0t18sEs4wTBBL_di | Egress / access | Move materials that are blocking access to flammables cabinets | Email Sent | 2026-01-24
2026-01-23 12:00 | nhh5@cornell.edu | Nhh5 | CUBMD | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1gwY0e1fP97A6wn3fchNxHbcOBaLPp_qo | Housekeeping | Clear team stuff from reservable table when not in use. | Email Sent | 2026-02-02
2026-01-23 12:04 | nhh5@cornell.edu | Nhh5 | EWB | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1FYy9H_zLArSs6XnS0tonCP7EtnjkWSjm | Housekeeping | Remove teams things from miserable table when not in use | Email Sent | 2026-02-02
2026-01-23 12:05 | nhh5@cornell.edu | Nhh5 | ESW | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1n9E8iMrdcuLE-S7YWD0QFdQPTbw_ASXM | Housekeeping | Remove team’s things from reservable table when not in use | Email Sent | 2026-02-02
2026-01-27 13:47 | nhh5@cornell.edu | Nhh5 | Steel Bridge | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1IiOsx9cC44RRxC1rZpDA9S1cAXw0-1dV | Egress / access | Please move as much of the metal stock as possible onto the lowest storage shelf and consolidate the rest to clear the walkway. | Email Sent | 2026-02-06
2026-01-29 13:04 | nhh5@cornell.edu | Nhh5 | AutoBoat | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1GeBWk2YHdB5lxc4Ks54YSWOsGuOgR29n | Egress / access | Move materials that are blocking the equipment in the hallway. Can relocate to basement of rhodes hall (storage cages) rhodes penthouse storage cages, or the high volt lab. Consult with operations staff. | Email Sent | 2026-02-01
2026-01-29 13:07 | nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1Sxgx7LoZNK5bS7JrQSzKlFpmebduI5MZ | Housekeeping | Move materials to storage. | Email Sent | 2026-02-08
2026-01-29 13:08 | nhh5@cornell.edu | Nhh5 | Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1dZBknIO9wAfF2yogyx4h_it3hjqU7Hb6 | Housekeeping | Move materials to storage. | Email Sent | 2026-02-08
2026-01-29 13:10 | nhh5@cornell.edu | Nhh5 | CUAir | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1Eur9CX_es2zhaRGL9CkYPvSJQryCmXBO | Housekeeping | Tidy up area, store chemicals and remove excess cardboard from upper shelving. | Email Sent | 2026-02-08
2026-01-29 13:15 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1VXHv8A1J6d84DRsp3ztoxUEPNsEWvIUt | Fire code | Store fuel and flammables (not in hot work area), clear access areas for eye wash and electrical panel. | Email Sent | 2026-01-30
2026-01-29 13:17 | nhh5@cornell.edu | Nhh5 | Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1ymY04ayEDichfhr93CXiBWvmyY-9MAy8 | Fire code | Move field test extinguishers to storage | Email Sent | 2026-01-30
2026-01-29 13:22 | nhh5@cornell.edu | Nhh5 | Formula | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1-5zH3kfAOTfFAemrPT6JUNMwQC2geGTL | Egress / access | Reroute cables to eliminate tripping hazard | Email Sent | 2026-02-01
2026-01-29 13:28 | nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1piiK5nWmTlQO2SDuG9uLGfZcZ3IfgQIm | Housekeeping | Tidy up hallway and toss recycling. | Email Sent | 2026-02-08
2026-01-29 13:30 | nhh5@cornell.edu | Nhh5 | Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1pMGblt_xj3L9UkKzdDwZa2Jzxiq5mozv | Housekeeping | Remove plywood from b60 | Email Sent | 2026-02-08
2026-02-02 10:30 | nhh5@cornell.edu | Nhh5 | Mars Rover | Ivory - Below Standards (address in 14-21 days) | https://drive.google.com/open?id=197mQTgsCe_4Lqls0jAUk_rnT5RKpErG2 | Housekeeping | Use shop vac to clean up sawdust/debris | Email Sent | 2026-02-23 | 2026-02-04
2026-02-03 16:28 | jam834@cornell.edu | jam834 | Unknown / unsure | Ivory - Below Standards (address in 14-21 days) | https://drive.google.com/open?id=1bdY0aZ9opcN6t_Jj0-7h8h1MDLdVi_ZL | Housekeeping | Area near paint booth needs picking up. Not sure which team's materials these are. |  | 2026-02-24
2026-02-03 16:31 | jam834@cornell.edu | jam834 | DEBUT | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1iOJWkEejMvijXob_rhDXUeHslAd4laYN | Egress / access | Wheelchair cannot be blocking the electrical panel. Chair moved out of the way. | Email Sent | 2026-02-06
2026-02-12 22:01 | nh428@cornell.edu | Nh428 | Unknown / unsure | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=12B-9rB2hdSCYwngV6_Ps2_-tBwbC_xsY | Fire code | Materials in fire lane, unsure of whose |  | 2026-02-15
2026-02-23 10:23 | nhh5@cornell.edu | Nhh5 | Concrete Canoe | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1G2Hax0RSCyVwEUURElK7o2C9EIR9KdDk | Housekeeping | Please pick up these new vacuums and dust control lids for the mix crew and bring them to the HVL ASAP | Email Sent | 2026-02-26
2026-02-23 16:32 | nhh5@cornell.edu | Nhh5 | CEV | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1dsW-H0n7DZvHBvsi6AOY_4LsJpGdsyRj | Fire code | Need to clean up CEV space in composites lab by end of day Wednesday for fire inspection. | Email Sent | 2026-02-26
2026-02-24 09:32 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1ki7v4nFCI88KEppqhRE-QyFNxWm_YwEM | Fire code | Clear panel access areas | Email Sent | 2026-02-25
2026-02-24 09:33 | nhh5@cornell.edu | Nhh5 | Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1nR7RLvHjbAS8MFvnLgpx2j1aRMe4P812 | Fire code | Move cones to avoid blocking extinguisher | Email Sent | 2026-02-25
2026-02-24 09:35 | nhh5@cornell.edu | Nhh5 | Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=11PKC4BzJgcJ6OxM43nSFywrXKQV-qj4Z | Fire code | Move materials to Rhodes basement cages or HVL to clear hallway | Email Sent | 2026-02-25
2026-02-24 09:36 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1ryDai6C-m7tpWQipCHZinxgjT5EwpJ3w | Fire code | Move materials to Rhodes storage or HVL to clear hallway | Email Sent | 2026-02-25
2026-02-24 09:39 | nhh5@cornell.edu | Nhh5 | CEV | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1to3zKfiqP5pSmoXTjMb11puq3qxbQUhk | Fire code | Clean up and organize composites space. Remove combustibles. Use Rhodes basement cages or HVL for storage if necessary | Email Sent | 2026-02-25
2026-02-24 09:41 | nhh5@cornell.edu | Nhh5 | Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1RWYNAcqHGg2S5swtIQFLLkbkRavyk9i_ | Fire code | Remove/ store material rolls | Email Sent | 2026-02-25
2026-02-24 09:42 | nhh5@cornell.edu | Nhh5 | Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=18aDWjAopFZClybVzoy9VYApFcTkAnhEr | Fire code | Clear floor as much as possible | Email Sent | 2026-02-25
2026-02-24 11:10 | nhh5@cornell.edu | Nhh5 | Design Build Fly | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1aLQZOt63rSPcMQdCmvzQe66XrebwpcgM | Fire code | Generator must be empty of fuel or moved to HVL or Rhodes penthouse | Email Sent | 2026-02-25
2026-02-24 11:58 | nhh5@cornell.edu | Nhh5 | Unknown / unsure | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1dAHvHu_sGzkcmCqsU--UuFco0dnsz7DR | Egress / access | Consolidate work area and clear aisle |  | 2026-03-06
2026-02-24 17:46 | jam834@cornell.edu | jam834 | Formula | Purple - Opportunity for improvement (as time permits) |  | Housekeeping | Coveralls should be placed into the cardboard bin containing the rest of them. The composites closet was organized recently but coveralls were strewn about the floor. | Email Sent | 2026-04-25
2026-02-26 09:18 | nhh5@cornell.edu | Nhh5 | Rocketry | Red - Code Compliance (same-day action Required) |  | Fire code | Please remove propane tank from inside HVL before 2pm today if at all possible. You can leave it in the back of the project truck if you need to. | Email Sent | 2026-02-27
2026-02-26 17:20 | nhh5@cornell.edu | Nhh5 | Concrete Canoe | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1infbLKH5ZD_R61t0DwNFnwvUNHASc9vt | Work Practices | Parts for your mix team vacuums are in Noah’s office. Pick them up any time. | Email Sent | 2026-04-27
2026-02-27 10:28 | nhh5@cornell.edu | Nhh5 | Rocketry | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1v_wL6ihOmYNmNpa0LP4SyI2JM7SoGNYP | Work Practices | Empty and return recycling container | Email Sent | 2026-03-02
2026-03-11 11:46 | nhh5@cornell.edu | Nhh5 | Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1ocbQXMShsQdXb2SaCoh1_dJXSU7IB2xF | Egress / access | Move cars onto Cornell property near HVL. | Email Sent | 2026-03-21
2026-03-11 11:47 | nhh5@cornell.edu | Nhh5 | CU Sail | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1gsRIqZ-1kiVnHYbPxfT1nURl-tigpH5i | Work Practices | Do not put hardening chemicals in paint funnel | Email Sent | 2026-03-21
2026-03-11 11:49 | nhh5@cornell.edu | Nhh5 | CU Sail | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1F82Tvx4SilRigp6eDacyCLzAEgyw-uFI | Work Practices | Clean up after work sessions so paints and chemicals don’t get tracked across floor. | Email Sent | 2026-03-21
2026-03-11 11:50 | nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) |  | Fire code | Please make signage to post on fire doors. |  | 2026-05-10 | 2026-05-12
2026-03-23 13:32 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1dUWD9AZ0oqOosQ33CrcMrOpY2daYJEtc | Housekeeping | Please collect boxes from mail room asap. | Email Sent | 2026-03-24
2026-03-25 09:26 | nhh5@cornell.edu | Nhh5 | CU Sail | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1XvsdCPXTvfjb9a21J4vl1XQqIMTGTpCI | Egress / access | Move boat and plywood stand asap so they do not block hallway. | Email Sent | 2026-03-26
2026-04-06 16:08 | nhh5@cornell.edu | Nhh5 | Mars Rover | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1_yoF506zHTqqo13tLAx5ooGjWFPE47GN | Egress / access | Disassemble and or move test stand in Rhodes basement. Can move to storage shelves in HVL | Email Sent | 2026-04-16
2026-04-14 12:09 | nhh5@cornell.edu | Nhh5 | Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1-ot_JLU13fRyngylhsY-gTNB_9h16agp | Fire code | Move drum blocking fire extinguisher and open up building egress path. | Email Sent | 2026-04-15
2026-04-14 12:10 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1hVGW4RTVkb3mmeajBbDi1odjULLxiaWG | Fire code | Clear access to eye wash | Email Sent | 2026-04-15
2026-04-14 12:12 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1WLHH2FiMXsCTwKRs9YALBLYZMLSsa0lb | Fire code | Clear access to panel and secure gas cylinder | Email Sent | 2026-04-15
2026-04-16 11:42 | nhh5@cornell.edu | Nhh5 | Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1NsfcWujvs3TTNRhilGEHClXymOREAUxF | Fire code | Clear access to eye wash. | Email Sent | 2026-04-17
2026-04-16 11:59 | nhh5@cornell.edu | Nhh5 | Rocketry | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1YMj0cKxb0eeWJV8k0_J-Y1PAr12tE_By | Fire code | Move propane bottle to loading dock and label | Email Sent | 2026-04-17
2026-04-24 09:44 | nhh5@cornell.edu | Nhh5 | Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=19DGewlgof6dncC8xL3R1sAWQLxyKGssZ | Shared space | Remove ‘baja’ paint from concrete wall | Email Sent | 2026-05-04
2026-04-28 09:43 | nhh5@cornell.edu | Nhh5 | Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1IJtwfoPELePLNDC96MM-gKSGtG8qLH7Z | Housekeeping | B60 is looking pretty rough and needs to be cleaned. Pick everything up off the floor so building care can clean the carpet and minimize greasy / fab activity | Email Sent | 2026-05-08
2026-04-28 09:45 | nhh5@cornell.edu | Nhh5 | CEV | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1YCHh_AFaNIsLQ9vebjX5Ikf4TZYaXtg5 | Shared space | Assuming this is CEVs should not be left in hallway. | Email Sent | 2026-05-01
2026-06-25 15:08 | nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1TcIPhgMmmaDuX0vUH89ZPDiJMOX4zieJ | Housekeeping | Disassemble wood frame (tools in Noah’s office.) |  | 2026-08-24
2026-06-25 15:09 | nhh5@cornell.edu | Mhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1sqCDzIixuUzJtndPY0POokvENF5GJD3q | Housekeeping | Move coolers, cart and shade canopies to penthouse. |  | 2026-08-24
2026-06-25 15:11 | nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1I3ZSYWb8dobHDzoMqXnvraed3Rd-BVH1 | Housekeeping | Unbolt pipe bender and stow behind spray booth in the hallway. |  | 2026-08-24
2026-06-25 15:13 | nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1XxOXx7Qf7b79VD6vZSTZ2gb40NxCj9Tm | Housekeeping | Move hard cases to penthouse |  | 2026-08-24
2026-06-26 09:12 | nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1V46lOtsseIaa18hiAJv2Gwd6QUfhCORO | Housekeeping | Cleanup and organize storage cages in Rhodes basement. |  | 2026-08-25
2026-06-26 09:15 | nhh5@cornell.edu | Nhh5 | Operations Team | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1-s9gPEfmxMBi3y0VKnIKd3DW327yANhJ | Housekeeping | Clean up spray booth. (Wear gloves and mask!) |  | 2026-08-25
2026-06-26 11:29 | nhh5@cornell.edu | Nhh5 | Combat Robotics | Purple - Opportunity for improvement (as time permits) | https://drive.google.com/open?id=1iclud4YzEUbdxx49NUqUydpRCkILVc-1 | Housekeeping | Testing- please forward the notification email to Noah at nhh5@cornell.edu | Email Sent | 2026-08-25

## Pending Actions
Highlight of pending actions - Avoid duplication of status reports - do not edit.
Team | Current Status | Photo | Required Actions / Comments | Deadline
Baja | Yellow - Stewardship concern (resolve in 7-10 days) | https://drive.google.com/open?id=1D3qL8TNVc7-zvT5jNVjWzs4qgRazBxpV | Please empty cabinet for relocation | 2025-11-10 | FALSE
EWH | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=16-2ZzgFD8n9wZYaniPOz0w6NisXEwoO_ | Assuming EWH. Wheelchair cannot be in front of the electrical panel. A note has been left on the chair by myself and I moved the chair on one occasion, but it keeps being replaced there. | 2025-11-16 | FALSE
EWH | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=18GFZyZDJ1WJcR3ieXj1Yw5iJKXofAb_- | Assuming EWH. Buckets / boxes cannot be placed in front of electrical panel. | 2025-11-16 | TRUE
Unknown / unsure | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1mQ8i67BWT-5bGibx-MAF1fsWzVJgi1QP | None of the Baja / FSAE team members I've spoken to know whose this crane is, but it is blocking the walkway / electrical panel. I have moved it once before, but it continues to be placed in this spot. | 2025-11-16 | FALSE
Geodata | Yellow - Stewardship Concern (resolve in 7-10 days) |  | Boxes appearing to contain geodata materials was placed in front of the EWH shelves. Please refrain from doing so and respect the storage areas of your fellow teams. The boxes were moved in front of the geodata shelves. | 2025-11-25 | TRUE
Formula | Yellow - Stewardship Concern (resolve in 7-10 days) |  | Store material rolls so the won’t fall or lean on waste chemical drum | 2025-12-01 | TRUE
AutoBoat | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=123AIpsKqNibRFF3EB1mKLcqO3XH4F6Ds | Remove materials that are blocking access to flammables cabinets | 2026-01-24 | TRUE
Formula | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1H96S9ivvB4e3WGdp0t18sEs4wTBBL_di | Move materials that are blocking access to flammables cabinets | 2026-01-24 | TRUE
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1VXHv8A1J6d84DRsp3ztoxUEPNsEWvIUt | Store fuel and flammables (not in hot work area), clear access areas for eye wash and electrical panel. | 2026-01-30 | TRUE
Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1ymY04ayEDichfhr93CXiBWvmyY-9MAy8 | Move field test extinguishers to storage | 2026-01-30 | TRUE
AutoBoat | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1GeBWk2YHdB5lxc4Ks54YSWOsGuOgR29n | Move materials that are blocking the equipment in the hallway. Can relocate to basement of rhodes hall (storage cages) rhodes penthouse storage cages, or the high volt lab. Consult with operations staff. | 2026-02-01 | FALSE
Formula | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1-5zH3kfAOTfFAemrPT6JUNMwQC2geGTL | Reroute cables to eliminate tripping hazard | 2026-02-01 | FALSE
CUBMD | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1gwY0e1fP97A6wn3fchNxHbcOBaLPp_qo | Clear team stuff from reservable table when not in use. | 2026-02-02 | FALSE
EWB | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1FYy9H_zLArSs6XnS0tonCP7EtnjkWSjm | Remove teams things from miserable table when not in use | 2026-02-02 | FALSE
ESW | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1n9E8iMrdcuLE-S7YWD0QFdQPTbw_ASXM | Remove team’s things from reservable table when not in use | 2026-02-02 | FALSE
Steel Bridge | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1IiOsx9cC44RRxC1rZpDA9S1cAXw0-1dV | Please move as much of the metal stock as possible onto the lowest storage shelf and consolidate the rest to clear the walkway. | 2026-02-06 | FALSE
DEBUT | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1iOJWkEejMvijXob_rhDXUeHslAd4laYN | Wheelchair cannot be blocking the electrical panel. Chair moved out of the way. | 2026-02-06 | TRUE
Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1Sxgx7LoZNK5bS7JrQSzKlFpmebduI5MZ | Move materials to storage. | 2026-02-08 | FALSE
Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1dZBknIO9wAfF2yogyx4h_it3hjqU7Hb6 | Move materials to storage. | 2026-02-08 | FALSE
CUAir | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1Eur9CX_es2zhaRGL9CkYPvSJQryCmXBO | Tidy up area, store chemicals and remove excess cardboard from upper shelving. | 2026-02-08 | FALSE
Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1piiK5nWmTlQO2SDuG9uLGfZcZ3IfgQIm | Tidy up hallway and toss recycling. | 2026-02-08 | FALSE
Formula | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1pMGblt_xj3L9UkKzdDwZa2Jzxiq5mozv | Remove plywood from b60 | 2026-02-08 | FALSE
Unknown / unsure | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=12B-9rB2hdSCYwngV6_Ps2_-tBwbC_xsY | Materials in fire lane, unsure of whose | 2026-02-15 | FALSE
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1ki7v4nFCI88KEppqhRE-QyFNxWm_YwEM | Clear panel access areas | 2026-02-25 | FALSE
Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1nR7RLvHjbAS8MFvnLgpx2j1aRMe4P812 | Move cones to avoid blocking extinguisher | 2026-02-25 | FALSE
Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=11PKC4BzJgcJ6OxM43nSFywrXKQV-qj4Z | Move materials to Rhodes basement cages or HVL to clear hallway | 2026-02-25 | FALSE
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1ryDai6C-m7tpWQipCHZinxgjT5EwpJ3w | Move materials to Rhodes storage or HVL to clear hallway | 2026-02-25 | FALSE
CEV | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1to3zKfiqP5pSmoXTjMb11puq3qxbQUhk | Clean up and organize composites space. Remove combustibles. Use Rhodes basement cages or HVL for storage if necessary | 2026-02-25 | FALSE
Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1RWYNAcqHGg2S5swtIQFLLkbkRavyk9i_ | Remove/ store material rolls | 2026-02-25 | FALSE
Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=18aDWjAopFZClybVzoy9VYApFcTkAnhEr | Clear floor as much as possible | 2026-02-25
Design Build Fly | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1aLQZOt63rSPcMQdCmvzQe66XrebwpcgM | Generator must be empty of fuel or moved to HVL or Rhodes penthouse | 2026-02-25
Concrete Canoe | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1G2Hax0RSCyVwEUURElK7o2C9EIR9KdDk | Please pick up these new vacuums and dust control lids for the mix crew and bring them to the HVL ASAP | 2026-02-26
CEV | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1dsW-H0n7DZvHBvsi6AOY_4LsJpGdsyRj | Need to clean up CEV space in composites lab by end of day Wednesday for fire inspection. | 2026-02-26
Rocketry | Red - Code Compliance (same-day action Required) |  | Please remove propane tank from inside HVL before 2pm today if at all possible. You can leave it in the back of the project truck if you need to. | 2026-02-27
Rocketry | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1v_wL6ihOmYNmNpa0LP4SyI2JM7SoGNYP | Empty and return recycling container | 2026-03-02
Unknown / unsure | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1dAHvHu_sGzkcmCqsU--UuFco0dnsz7DR | Consolidate work area and clear aisle | 2026-03-06
Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1ocbQXMShsQdXb2SaCoh1_dJXSU7IB2xF | Move cars onto Cornell property near HVL. | 2026-03-21
CU Sail | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1gsRIqZ-1kiVnHYbPxfT1nURl-tigpH5i | Do not put hardening chemicals in paint funnel | 2026-03-21
CU Sail | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1F82Tvx4SilRigp6eDacyCLzAEgyw-uFI | Clean up after work sessions so paints and chemicals don’t get tracked across floor. | 2026-03-21
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1dUWD9AZ0oqOosQ33CrcMrOpY2daYJEtc | Please collect boxes from mail room asap. | 2026-03-24
CU Sail | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1XvsdCPXTvfjb9a21J4vl1XQqIMTGTpCI | Move boat and plywood stand asap so they do not block hallway. | 2026-03-26
Formula | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1-ot_JLU13fRyngylhsY-gTNB_9h16agp | Move drum blocking fire extinguisher and open up building egress path. | 2026-04-15
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1hVGW4RTVkb3mmeajBbDi1odjULLxiaWG | Clear access to eye wash | 2026-04-15
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1WLHH2FiMXsCTwKRs9YALBLYZMLSsa0lb | Clear access to panel and secure gas cylinder | 2026-04-15
Mars Rover | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1_yoF506zHTqqo13tLAx5ooGjWFPE47GN | Disassemble and or move test stand in Rhodes basement. Can move to storage shelves in HVL | 2026-04-16
Baja | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1NsfcWujvs3TTNRhilGEHClXymOREAUxF | Clear access to eye wash. | 2026-04-17
Rocketry | Red - Code Compliance (same-day action Required) | https://drive.google.com/open?id=1YMj0cKxb0eeWJV8k0_J-Y1PAr12tE_By | Move propane bottle to loading dock and label | 2026-04-17
CEV | Orange - Operations Safety (resolve in 2-3 business days) | https://drive.google.com/open?id=1YCHh_AFaNIsLQ9vebjX5Ikf4TZYaXtg5 | Assuming this is CEVs should not be left in hallway. | 2026-05-01
Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=19DGewlgof6dncC8xL3R1sAWQLxyKGssZ | Remove ‘baja’ paint from concrete wall | 2026-05-04
Baja | Yellow - Stewardship Concern (resolve in 7-10 days) | https://drive.google.com/open?id=1IJtwfoPELePLNDC96MM-gKSGtG8qLH7Z | B60 is looking pretty rough and needs to be cleaned. Pick everything up off the floor so building care can clean the carpet and minimize greasy / fab activity | 2026-05-08

## (WIP) Dashboard v2
Refer to Analyses Subsheet for source data

## (WIP) Analysis
Team Name | Issue Type | Issue Severity | Date | Assigned Week # | Full Size Charts on Dashboard v2 | Week # | Num. Issues
#REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 6
#REF! | #REF! | #REF! | #REF! | #REF! |  | 1 | 0
#REF! | #REF! | #REF! | #REF! | #REF! |  | 2 | 7
#REF! | #REF! | #REF! | #REF! | #REF! |  | 3 | 0
#REF! | #REF! | #REF! | #REF! | #REF! |  | 4 | 0
#REF! | #REF! | #REF! | #REF! | #REF! |  | 5 | 0
#REF! | #REF! | #REF! | #REF! | #REF! |  | 6 | 0
steel bridge | Housekeeping | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-09-18 09:20 | 0 |  | 7 | 0
concrete canoe | Shared space (misuse of) | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-09-18 09:24 | 0 |  | 8 | 0
Formula | Shared space (misuse of) | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-09-18 09:29 | 0 |  | 9 | 0
concrete canoe | Housekeeping | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-09-18 09:33 | 0 |  | 10 | 0
Formula | Shared space (misuse of) | Orange - Operations/ Safety issue (resolve in 2-3 business days) | 2025-09-18 14:54 | 0 |  | 11 | 0
concrete canoe | Fire / electrical (code violation) | Red - Code violation (immediate action Required) | 2025-09-19 17:14 | 0 |  | 12 | 0
Mars Rover | Egress / access | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-10-02 15:18 | 2 |  | 13 | 0
DEBUT | Fire / electrical (code violation) | Red - Code violation (immediate action Required) | 2025-10-02 16:41 | 2 |  | 14 | 0
Operations Team | Unsafe Work Practices | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-10-03 09:13 | 2 |  | 15 | 0
Operations Team | Maintenance/ facilities | Ivory - Below standard (demonstrate improvement in 14-21 days) | 2025-10-03 09:30 | 2 |  | 16 | 0
Operations Team | Unsafe Work Practices | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-10-03 09:33 | 2 |  | 17 | 0
Operations Team | Fire / electrical (code violation) | Yellow - Stewardship concern (Address at next scheduled meeting) | 2025-10-03 09:35 | 2 |  | 18 | 0
Operations Team | Maintenance/ facilities | Purple - Opportunity for improvement (as time permits) | 2025-10-03 09:40 | 2 |  | 19 | 0
[6 empty] | 20 | 0
[6 empty] | 21 | 0
[6 empty] | 22 | 0
[6 empty] | 23 | 0
[6 empty] | 24 | 0
[6 empty] | 25 | 0
[6 empty] | 26 | 0
[6 empty] | 27 | 0
[6 empty] | 28 | 0
[6 empty] | 29 | 0
[6 empty] | 30 | 0
[6 empty] | 31 | 0
[6 empty] | 32 | 0
[6 empty] | 33 | 0
[6 empty] | 34 | 0
[6 empty] | 35 | 0
[6 empty] | 36 | 0
[6 empty] | 37 | 0
[6 empty] | 38 | 0
[6 empty] | 39 | 0
[6 empty] | 40 | 0
[6 empty] | 41 | 0
[6 empty] | 42 | 0
[6 empty] | 43 | 0
[6 empty] | 44 | 0
[6 empty] | 45 | 0
[6 empty] | 46 | 0
[6 empty] | 47 | 0
[6 empty] | 48 | 0
[6 empty] | 49 | 0
[6 empty] | 50 | 0
[6 empty] | 51 | 0
[6 empty] | 52 | 0
[6 empty] | 53 | 0
[6 empty] | 54 | 0
[6 empty] | 55 | 0
[6 empty] | 56 | 0
[6 empty] | 57 | 0
[6 empty] | 58 | 0
[6 empty] | 59 | 0
[6 empty] | 60 | 0
[6 empty] | 61 | 0
[6 empty] | 62 | 0
[6 empty] | 63 | 0
Formulas:
Assigned Week # = WEEKNUM([Date])-38

## Team Contacts
Team Name | Form Name | Location | Email Address | Notes
AguaClara | AguaClara | Unassigned | aguaclara@cornell.edu
AppDev | AppDev | Unassigned | team@cornellappdev.com
AutoBoat | AutoBoat | ELL | cornellautoboat@gmail.com
Autonomous Drone | Autonomous Drone | Unassigned | cuautodrone@gmail.com | Location unknown
Autonomous Sailboat | CU Sail | ELL | cusail@cornell.edu
Autonomous Underwater Vehicle | CUAUV | ELL | cuauvleader@gmail.com
Baja | Baja | ELL | baja@cornell.edu
Biomedical Device | CUBMD | ELL | cubmd@gmail.com | Assigned to reservable bench
ChemE Car | ChemE Car | ELL | cuchemecar@cornell.edu | Emailed listed is for "business inquires"
Combat Robotics | Combat Robotics | ELL | combatrobotics@cornell.edu
Concrete Canoe | Concrete Canoe | HVL | concrete-canoe@cornell.edu
Cornell Assistive Technologies | Cornell Assistive Technologies | ELL | cornellassist@gmail.com
Unmanned Air System | CUAir | ELL | cuair.mae@gmail.com
Custom Silicon Systems | Custom Silicon Systems | Unassigned | c2s2@cornell.edu
Data Science | Data Science | Unassigned | cornelldatascience@gmail.com
DEBUT | DEBUT | ELL | debut@cornell.edu
Design Build Fly | Design Build Fly | ELL | designbuildfly@cornell.edu
Digtal Tech and Innovation | Digtal Tech and Innovation | Unassigned | hello@cornelldti.org | Verify email (if necessary)
Electric Vehicles | CEV | ELL | cornellev@cornell.edu
Engineering World Health | EWH | ELL | ewhcornell@gmail.com
Engineerings Without Boarders | EWB | Unassigned | ewbcornell@gmail.com
Engineers for a Sustainable World | ESW | ELL | eswprojectteam@cornell.edu
Engineers in Action | Engineers in Action | ELL | eiacornelluniversity@gmail.com
Extended Reality | Extended Reality | ELL | cornellxrclub@gmail.com
FSAE Racing | Formula | Auto | cufsae@cornell.edu
GeoData | Geodata | ELL | cugeodatateam@gmail.com
Hack4Impact | Hack4Impact | Unassigned | cornell@hack4impact.org
Hyperloop | Hyperloop | ELL | cornellhyperloop@gmail.com
iGEM | iGEM | ELL | cornelligem@gmail.com
Mars Rover | Mars Rover | ELL | cornellmarsrover@gmail.com
Nexus | Nexus | ELL | nexus@cornell.edu
Rocketry | Rocketry | ELL | rocketry@cornell.edu
Seismic Design | Seismic Design | ELL | hfj46@cornell.edu | No team email listed; this email is for a lead.
SensTech | SensTech | Unassigned | cornellsenstech@gmail.com
Solar Boat | Solar Boat | ELL | solarboatcornell@gmail.com
Steel Bridge | Steel Bridge | HVL | steelbridge@cornell.edu | Confirm location